## Gantt Chart
Project #2 - GANTT CHART
PROJECT TITLE |  | CIVE 202 PROJECT #2 |  |  |  |  | COMPANY NAME | [6 empty] | Group 151-06
PROJECT MANAGER |  | Addison Jehorek, Jamie Krab, Jessica Tackett, Tessa Soukup |  |  |  |  | START DATE | [6 empty] | 2026-02-09
[7 empty] | END DATE | [6 empty] | 2026-02-24
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | WEEK 1 (2/9-2/13) |  |  |  |  | WEEK 2 (2/16-2/20) |  |  |  |  | WEEK 3 (2/23-2/27)
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Data Processing
1.1 | Create Gantt Chart | Addison J | 2026-02-09 | 2026-02-13 | 4 | 100% | bar: WEEK 1 (2/9-2/13) R to WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R
1.1.1 | Read and Understand Client Prompt | Jamie K | 2026-02-09 | 2026-02-13 | 4 | 100% | bar: WEEK 1 (2/9-2/13) R to WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R
1.2 | Complete Additional Necessary Research | Jessica T | 2026-02-09 | 2026-02-15 | 6 | 100% | bar: WEEK 1 (2/9-2/13) F to WEEK 2 (2/16-2/20) T; WEEK 2 (2/16-2/20) R
2 | Scope of Work
2.1 | Write Project Goals | Tessa S | 2026-02-13 | 2026-02-16 | 3 | 100% | bar: WEEK 1 (2/9-2/13) F to WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R
2.2 | Write Project Tasks | Addison J | 2026-02-13 | 2026-02-16 | 3 | 100% | bar: WEEK 1 (2/9-2/13) F to WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R
2.3 | Write Project Deliverables | Jamie K | 2026-02-13 | 2026-02-16 | 3 | 100% | bar: WEEK 1 (2/9-2/13) F to WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R
2.4 | Finialize SOW | Jessica T | 2026-02-16 | 2026-02-19 | 4 | 100% | bar: WEEK 2 (2/16-2/20) M to WEEK 2 (2/16-2/20) R
3 | Scenario Development
3.1 | Evaluate first concrete mix desing scenario in automated Python Model | Tessa S | 2026-02-16 | 2026-02-18 | 2 | 100% | bar: WEEK 2 (2/16-2/20) M to WEEK 2 (2/16-2/20) R
3.2 | Evaluate second concrete mix desing scenario in automated Python Model | Addison J | 2026-02-17 | 2026-02-19 | 2 | 100% | bar: WEEK 2 (2/16-2/20) M to WEEK 2 (2/16-2/20) R
3.2.1 | Evaluate third concrete mix desing scenario in automated Python Model | Jamie K | 2026-02-18 | 2026-02-20 | 2 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) W to WEEK 2 (2/16-2/20) F
3.2.2 | Evaluate fourth concrete mix desing scenario in automated Python Model | Jessica T | 2026-02-19 | 2026-02-21 | 2 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R to WEEK 2 (2/16-2/20) F
4 | Python Code
4.1 | Project #2 - Week 4 lab | All | 2026-02-06 | 2026-02-06 | 0 | 100% | bar: WEEK 1 (2/9-2/13) F to WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R
4.2 | Project #2 - Week 5 lab | All | 2026-02-13 | 2026-02-13 | 0 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R to WEEK 2 (2/16-2/20) F
4.3 | Project #2 - Week 6 lab | All | 2026-02-20 | 2026-02-20 | 0 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R; WEEK 3 (2/23-2/27) F
4.4 | Work on the final Project #2 Code | All | 2026-02-13 | 2026-02-21 | 8 | 100% | bar: WEEK 2 (2/16-2/20) M to WEEK 2 (2/16-2/20) R
4.4 | - Translate Excel logic into python | Jessica T | 2026-02-13 | 2026-02-17 | 4 | 100% | bar: WEEK 2 (2/16-2/20) M to WEEK 2 (2/16-2/20) R
4.4 | - Implement sequential user inputs | Jessica T | 2026-02-17 | 2026-02-19 | 2 | 100% | bar: WEEK 2 (2/16-2/20) M to WEEK 2 (2/16-2/20) R
4.4 | - Generate a final mix design output | Jessica T | 2026-02-17 | 2026-02-20 | 3 | 100% | bar: WEEK 2 (2/16-2/20) M to WEEK 2 (2/16-2/20) R
5 | Results Validation
5.1 | Write Introduction/Background of Technical Report | Tessa S | 2026-02-14 | 2026-02-17 | 3 | 100% | bar: WEEK 2 (2/16-2/20) M to WEEK 2 (2/16-2/20) T; WEEK 2 (2/16-2/20) R
5.2 | Write Methods (Excel to Python traslation and parameters) of Technical Report | Addison J | 2026-02-19 | 2026-02-23 | 4 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R to WEEK 3 (2/23-2/27) M
5.3 | Write Results/Discussion of Technical Report | Jamie K | 2026-02-19 | 2026-02-23 | 4 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R to WEEK 3 (2/23-2/27) M
5.4 | Write Reference List of Technical Report | Jessica T | 2026-02-16 | 2026-02-17 | 1 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R
6 | Annotated Code Document
6.1 | Review the finished Python Code | Tessa S | 2026-02-19 | 2026-02-20 | 1 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R to WEEK 2 (2/16-2/20) F
6.2 | Assign parts of the code to annotate for each team member | Addison J | 2026-02-20 | 2026-02-20 | 0 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R to WEEK 2 (2/16-2/20) F
6.3 | Complete the Annontated Code Document | Jamie K | 2026-02-20 | 2026-02-23 | 3 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R to WEEK 3 (2/23-2/27) M
7 | Project 2 Reflection
7.1 | Put all documents and links into GitHub including the code, data, and a README file | All | 2026-02-23 | 2026-02-24 | 1 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R; WEEK 3 (2/23-2/27) W to WEEK 3 (2/23-2/27) R
7.2 | Reflection Quiz | All | 2026-02-24 | 2026-02-27 | 3 | 100% | bar: WEEK 2 (2/16-2/20) M; WEEK 2 (2/16-2/20) R; WEEK 3 (2/23-2/27) F